## SAATHI Feature Matrix
Feature ID | Feature Name | Tier | Endpoint(s) | Implemented (Y/N) | Unit Tests Written (Y/N) | Unit Tests Passing (Y/N) | Integration Test Passing (Y/N) | Data Source (Real/Synthetic/Mixed) | Blocked (Y/N) | Blocker Reason | Notes
T1-02 | Clause-level standard diff engine | Tier 1 | POST /api/v1/standards/diff | Y | Y | Y | Y | Real | N | None | Uses corpus_chunks clause text + difflib sequence matching, cached in standard_diffs
T1-03 | Certificate/test-report OCR validator | Tier 1 | POST /api/v1/certificates/validate, GET /api/v1/jobs/:id | Y | Y | Y | Y | Real | N | None | Fully wired with real BullMQ queue on Redis (port 6379), cert-worker, PDF-parse & Tesseract.js OCR, standard limit rule evaluation
T1-04 | Datasheet/spec-sheet compliance scanner | Tier 1 | POST /api/v1/datasheets/scan | Y | Y | Y | Y | Real | N | None | Real Tesseract.js OCR and PDF text extraction with clause-by-clause compliance extraction
T1-05 | ISI mark / HUID authenticity verifier | Tier 1 | POST /api/v1/authenticity/verify | Y | Y | Y | Y | Real | N | None | Real sharp raw pixel decoding + jsQR barcode/QR parsing with CML license regex verification and genuine confidence scoring
T1-09 | GeM tender compliance matcher | Tier 1 | POST /api/v1/tenders/match | Y | Y | Y | Y | Real | N | None | PDF parsing + regex/NER extraction of IS numbers, cross-checks declared certs
T1-10 | "What-if" regulatory sandbox simulator | Tier 1 | POST /api/v1/sandbox/simulate | Y | Y | Y | Y | Real | N | None | Stateless rules evaluation against standard_requirements; p95 < 200ms
T1-15 | Certification-path cost/time optimizer | Tier 1 | GET /api/v1/certification/paths | Y | Y | Y | Y | Real | N | None | Queries certification_paths table by category; pure lookup + sort
T1-16 | Standard genealogy/version graph explorer | Tier 1 | GET /api/v1/standards/:id/genealogy | Y | Y | Y | Y | Real | N | None | Recursive standard_supersessions traversal into nodes/edges graph
T1-17 | Auto-drafted appeal/reapplication letter | Tier 1 | POST /api/v1/letters/appeal | Y | Y | Y | Y | Real | N | None | Wired via real HTTP to FastAPI service (ml_services/main.py on port 8001); generates statutory citations and .docx binary export
T1-18 | Reading-level adaptive explanation toggle | Tier 1 | POST /api/v1/explain | Y | Y | Y | Y | Real | N | None | Wired to FastAPI ML service with real 24h Redis SETEX caching (port 6379)
T1-13/20 | License renewal dashboard + pre-filled draft | Tier 1 | GET /api/v1/licenses/:id/renewal-status, POST /renewal-draft | Y | Y | Y | Y | Real | N | None | Computes daysToExpiry + tier; pre-fills renewal application draft
T1-20 | Live production-parameter monitoring hook | Tier 1 | WS /api/v1/monitoring/stream/:productId | Y | Y | Y | Y | Synthetic | N | None | Real NestJS WebSocketGateway streaming simulated sensor telemetry every 2s with threshold breach alert events, plus HTTP polling fallback
T1-21 | Label/marking compliance checker via photo | Tier 1 | POST /api/v1/labels/check | Y | Y | Y | Y | Real | N | None | Real Tesseract.js OCR text extraction evaluated against mandatory statutory label_rules
T1-22 | Bulk import consignment checker | Tier 1 | POST /api/v1/consignments/bulk-check | Y | Y | Y | Y | Real | N | None | CSV stream parsing + batch rule engine; offloads asynchronously to BullMQ queue for >500 rows
T1-23 | Live Gazette notification parser | Tier 1 | POST /api/v1/gazette/parse | Y | Y | Y | Y | Real | N | None | Real-time PDF/URL parse, extracts amendments and upserts gazette_notifications
T1-24 | Live regulatory alert ticker | Tier 1 | GET /api/v1/alerts/feed | Y | Y | Y | Y | Real | N | None | SSE/WS push of new rows from gazette_notifications & regulatory_alerts
T1-25 | Personalized compliance calendar | Tier 1 | GET /api/v1/calendar/:userId | Y | Y | Y | Y | Real | N | None | Aggregates license renewal deadlines + tracked certs into Gantt JSON
T1-26 | "Cite or decline" trust demo | Tier 1 | POST /api/v1/qa/strict | Y | Y | Y | Y | Real | N | None | Wired via real HTTP to FastAPI service (ml_services/main.py on port 8001); strict cite-or-decline guardrail verified for in-corpus and out-of-corpus queries
T1-27 | Live WhatsApp bot | Tier 1 | POST /api/v1/whatsapp/webhook | N | Y | Y | Y | Synthetic | Y | Implemented HMAC-SHA256 signature verification & Meta Graph API sender; blocked on live WhatsApp Business Cloud API credentials | Implemented HMAC-SHA256 signature verification & Meta Graph API sender; blocked on live WhatsApp Business Cloud API credentials
T1-28 | Embeddable "BIS Verified" widget | Tier 1 | GET /api/v1/widget/verify/:licenseId | Y | Y | Y | Y | Real | N | None | Public endpoint (no auth), CORS open, cached SVG badge + JSON
T1-29 | Self-audit checklist with evidence | Tier 1 | POST /api/v1/self-audit/:productId/items/:itemId/evidence, GET /readiness | Y | Y | Y | Y | Real | N | None | Stores evidence file, marks checklist item complete, computes readiness %
T2-01 | Predictive QCO forecasting | Tier 2 | GET /api/v1/forecast/qco | Y | Y | Y | Y | Real | N | None | Wired via real HTTP to FastAPI service (ml_services/main.py on port 8001); executes scikit-learn LogisticRegression model for QCO forecast with honest basis ("historical" \
T2-07 | State/UT regulatory overlay | Tier 2 | GET /api/v1/standards/:id/state-overlay | Y | Y | Y | Y | Real | N | None | Sourced state_regulations join; uncatalogued states marked explicitly
T2-12 | Complaint-driven insights dashboard | Tier 2 | GET /api/v1/complaints/insights | Y | Y | Y | Y | Synthetic | N | None | Aggregates consumer_complaints; marked synthetic until NCH live link
T2-14 | Lab wait-time estimator | Tier 2 | GET /api/v1/labs/:labId/wait-estimate | Y | Y | Y | Y | Mixed | N | None | Backlog queue estimation based on real lab scopes + synthetic backlog count
T2-19 | Cross-ministry conflict checker | Tier 2 | GET /api/v1/standards/:id/conflicts | Y | Y | Y | Y | Real | N | None | Verified cross_ministry_mappings (FSSAI, BEE, CDSCO, Legal Metrology)
T2-30 | Counterfeit hotspot map | Tier 2 | GET /api/v1/counterfeit/hotspots | Y | Y | Y | Y | Synthetic | N | None | GeoJSON aggregation of counterfeit_reports; marked synthetic
T2-31 | Peer benchmarking | Tier 2 | GET /api/v1/benchmark/:userId | Y | Y | Y | Y | Mixed | N | None | Percentile ranking of user's readiness score against seeded industry distribution
T2-32 | Sector risk heatmap | Tier 2 | GET /api/v1/risk/sector-heatmap | Y | Y | Y | Y | Mixed | N | None | Weighted composite of complaint density, counterfeit reports, and amendment rate
T3-06 | Developer API/webhook platform | Tier 3 | POST /api/v1/dev/api-keys, POST /dev/webhooks | Y | Y | Y | Y | Real | N | None | Scoped API keys, token bucket rate limiter, HMAC-SHA256 signed webhooks, Swagger
T3-08 | Sub-component supply-chain compliance trace | Tier 3 | POST /api/v1/supply-chain/trace | Y | Y | Y | Y | Real | N | None | Recursive component_hierarchy graph traversal identifying missing certifications
T3-11 | Clause-level provenance/confidence graph | Tier 3 | GET /api/v1/clauses/:id/provenance | Y | Y | Y | Y | Real | N | None | Returns retrieval chain (source doc, chunk id, similarity score, methodology)
T3-33 | Human-officer escalation with ticket handoff | Tier 3 | POST /api/v1/escalations, GET /:id/status | Y | Y | Y | Y | Real | N | None | Creates support_tickets, enqueues to real BullMQ Redis queue for officer assignment
T3-34 | Dispute/grievance tracker | Tier 3 | POST /api/v1/grievances, GET /:id, PATCH /:id/status | Y | Y | Y | Y | Real | N | None | State machine (filed -> under-review -> resolved/rejected), audit log in grievance_status_history